Troop 615

Outing Timeline – Step 2

Once you have completed the Outing Planning Survey, you will have a good idea of what you need to accomplish.  This sheet is to help you chart out the timing of your planning, and, if used properly, it should keep you on track. It will be used along with the Outing Plan – Part 3.

Outing: __________________________________ Scheduled Date: __________________

Patrol Name: ______________________________Patrol Leader: ___________________

| Target Date | Lead Time | Action | Completion Date |
| --- | --- | --- | --- |
|  | 2 weeks after SPC | Complete the Outing Survey – Step 1 Check in with SPL and Scoutmaster to show them what you are planning. Adjust plan to address any concerns. Repeat as necessary. |  |
|  | 3-12 months, Maybe more | Reserve facility as necessary (work with Activity Coordinators) Confirmation Number: __________________ Point of Contact: __________________________ |  |
|  | 2-6 months | Does the troop need to update medical exam forms before the outing? (usually done before summer camp) |  |
|  | 2 -6 months | Begin promoting your outing to the troop. Start with very general info, to get scouts interested, and add details as the weeks unfold. Use meetings and emails. Mention it every meeting once you are inside of 2 months. |  |
|  | 6 weeks | Complete the Outing Plan – Step 3 This will contain answers to all of the details you will need to address. Share the plan with the SPL and Scoutmaster so they can share at PLC. |  |
|  | 5 weeks | If you desire the SPL to help the troop prepare certain skills for the outing, submit a plan of instruction to him so he can schedule time at meetings for it. This would come up for Snow Caving, Camporees, etc. |  |
|  | 5 weeks | Work with the Activities Coordinators to send out permission slips. Send it out via email, but also have some hard copies at meetings. Can be done earlier. |  |
|  | 5 weeks | Send any info you have typed up on your outing to the webmaster via email so he can help you promote your outing on the website. (Fliers, permission slips, web links, photos, whatever. The more the better.) |  |
|  | 5 weeks | Recruit adult help/drivers for outing. Activities Coordinators can help you with this. Make sure you have enough car seats for scouts. |  |
|  | 5 weeks | Provide Outing Plan to the Activities Coordinators so they can start the BSA Tour Plan. |  |
|  | 5 weeks | Identify a driver to pull the trailer (if you are taking it) |  |
|  | 5 weeks | Ask Troop Scribe to put info about the outing in the troop minutes. |  |
|  | 5 weeks | Have an Outing Roster ready to go to record scout names as they bring you permission slips and money. |  |
|  | 3 weeks | As outing coordinator, make a checklist for yourself of troop gear to pack for the outing (first aid kit, propane tanks, stoves, troop flags and sign, etc.). Provide a copy to the Quartermaster. |  |
|  | 3 weeks | Confirm any reservations you made earlier. |  |
|  | 3 weeks | Speak with Troop Quartermaster about any equipment concerns you have. Ask him to check propane tanks if you are taking them. |  |
|  | 3 weeks | Speak with Chaplain’s Aide to plan a Sunday service (if applicable) |  |
|  | 2 weeks | Patrols plan meals, skits, anything else patrol related for outing. |  |
|  | 2 weeks | Deadline for turning in permission slips (two Mondays before the outing). Exceptions may be made only by the SPL or Scoutmaster |  |
|  | 2 weeks | Confirm with the Activities Coordinators that the Tour Permit is approved. |  |
|  | 2 weeks | Confirm with Patrol Leaders: “Ready to Go?” |  |
|  | 2 weeks | Speak with Troop Historian to see about photo coverage of the outing. |  |
|  | 1 week | Make Driving Directions for drivers – hand out at meeting in advance. Have extra copies available the day of departure. MapQuest works well. |  |
|  | 1 week | Email attendees about departure time, packing considerations, or anything else on your mind. |  |
|  | 1 week | Confirm that each of your drivers is still available. |  |
|  | 1 week | Look over your checklist of troop gear – do you have everything ready to go for day of departure? |  |
|  | Day of Departure | Bring permission slips and tour permit with you. Also bring any paperwork you have for your outing (reservations), and a copy of the Guide to Safe Scouting. |  |
|  | Day of Departure | Take roll using your Outing Roster and make sure all scouts and drivers are present or accounted for. (some may have arranged to come later) |  |
|  | Day of Departure | Ensure Troop gear is packed. |  |
|  | Day of Departure | Speak with each patrol leader and ensure they have patrol gear and food packed. |  |
|  | Day of Departure | Provide drivers with directions and assign cars for scouts. Head out! Have a great Outing. |  |
|  | Upon Return | Make sure Troop Gear is properly dried out, cleaned, and restowed by the troop. |  |
|  | Upon Return | Forward a copy of your roster of all attendees, scouts and adults, to the Scoutmaster by email or hard copy. (used for record keeping) Income/Expense report goes to the troop treasurer. |  |
|  | Upon Return | Prepare and send any necessary Thank You notes to individuals outside the troop that helped you with your outing. |  |